## Sheet1
Entrant Stories | ID | User Story | Story Points | Risk | Halfway Checkpoint
| US 01.01.01 | As an entrant, I want to join the waiting list for a specific event | 3 | M | Yes
| US 01.01.02 | As an entrant, I want to leave the waiting list for a specific event | 2 | L | Yes
| US 01.01.03 | As an entrant, I want to be able to see a list of events that I can join the waiting list for. | 3 | L | Yes
| US 01.01.04 | As an entrant, I want to filter events based on my interests and availability. | 5 | M | No
| US 01.02.01 | As an entrant, I want to provide my personal information such as name, email and optional phone number in the app | 3 | L | Yes
| US 01.02.02 | As an entrant I want to update information such as name, email and contact information on my profile | 2 | L | Yes
| US 01.02.03 | As an entrant, I want to have a history of events I have registered for, whether I was selected or not. | 5 | M | No
| US 01.02.04 | As an entrant, I want to delete my profile if I no longer wish to use the app. | 2 | M | No
| US 01.04.01 | As an entrant I want to receive notification when I am chosen to participate from the waiting list (when I "win" the lottery) | 3 | M | Yes
| US 01.04.02 | As an entrant I want to receive notification of when I am not chosen on the app (when I "lose" the lottery) | 3 | M | Yes
| US 01.04.03 | As an entrant I want to opt out of receiving notifications from organizers and admins | 3 | M | No
| US 01.05.01 | As an entrant I want another chance to be chosen from the waiting list if a selected user declines an invitation to sign up. | 5 | H | No
| US 01.05.02 | As an entrant I want to be able to accept the invitation to register/sign up when chosen to participate in an event. | 3 | M | Yes
| US 01.05.03 | As an entrant I want to be able to decline an invitation when chosen to participate in an event. | 3 | M | Yes
| US 01.05.04 | As an entrant, I want to know how many total entrants are on the waiting list for an event. | 2 | L | No
| US 01.05.05 | As an entrant, I want to be informed about the criteria or guidelines for the lottery selection process. | 1 | L | Yes
| US 01.06.01 | As an entrant I want to view event details within the app by scanning the promotional QR code. | 5 | M | Yes
| US 01.06.02 | As an entrant I want to be able to be sign up for an event by from the event details. | 3 | M | Yes
| US 01.07.01 | As an entrant, I want to be identified by my device, so that I don't have to use a username and password. | 5 | H | No
Organizer Stories | ID | User Story | Story Points | Risk | Halfway Checkpoint
| US 02.01.01 | As an organizer I want to create a new event and generate a unique promotional QR code that links to the event description and event poster in the app. | 8 | H | Yes
| US 02.01.04 | As an organizer, I want to set a registration period. | 3 | L | Yes
| US 02.02.01 | As an organizer I want to view the list of entrants who joined my event waiting list | 3 | L | Yes
| US 02.02.02 | As an organizer I want to see on a map where entrants joined my event waiting list from. | 5 | H | No
| US 02.02.03 | As an organizer I want to enable or disable the geolocation requirement for my event. | 3 | M | No
| US 02.03.01 | As an organizer I want to OPTIONALLY limit the number of entrants who can join my waiting list. | 2 | L | No
| US 02.04.01 | As an organizer I want to upload an event poster to the event details page to provide visual information to entrants. | 5 | M | Yes
| US 02.04.02 | As an organizer I want to update an event poster to provide visual information to entrants. | 2 | L | No
| US 02.05.01 | As an organizer I want to send a notification to chosen entrants to sign up for events. | 3 | M | Yes
| US 02.05.02 | As an organizer I want to set the system to sample a specified number of attendees to register for the event. | 5 | H | No
| US 02.05.03 | As an organizer I want to be able to draw a replacement applicant from the pooling system when a previously selected applicant cancels or rejects the invitation. | 8 | H | No
| US 02.06.01 | As an organizer I want to view a list of all chosen entrants who are invited to apply. | 3 | M | Yes
| US 02.06.02 | As an organizer I want to see a list of all the cancelled entrants. | 3 | L | No
| US 02.06.03 | As an organizer I want to see a final list of entrants who enrolled for the event. | 3 | L | No
| US 02.06.04 | As an organizer I want to cancel entrants that did not sign up for the event | 3 | M | No
| US 02.06.05 | As an organizer I want to export a final list of entrants who enrolled for the event in CSV format. | 5 | M | No
| US 02.07.01 | As an organizer I want to send notifications to all entrants on the waiting list | 3 | M | No
| US 02.07.02 | As an organizer I want to send notifications to all selected entrants | 2 | L | No
| US 02.07.03 | As an organizer I want to send a notification to all cancelled entrants | 2 | L | No
Admin Stories | ID | User Story | Story Points | Risk | Halfway Checkpoint
| US 03.01.01 | As an administrator, I want to be able to remove events. | 3 | M | Yes
| US 03.02.01 | As an administrator, I want to be able to remove profiles. | 3 | M | Yes
| US 03.03.01 | As an administrator, I want to be able to remove images. | 3 | M | No
| US 03.04.01 | As an administrator, I want to be able to browse events. | 3 | L | Yes
| US 03.05.01 | As an administrator, I want to be able to browse profiles. | 3 | L | Yes
| US 03.06.01 | As an administrator, I want to be able to browse images that are uploaded so I can remove them if necessary. | 3 | M | No
| US 03.07.01 | As an administrator I want to remove organizers that violate app policy. | 5 | H | No
| US 03.08.01 | As an administrator, I want to review logs of all notifications sent to entrants by organizers. | 5 | M | No